## Sheet1
Task | Task Detail Description | Priority | Status | Environment | Phase | Hours | Timeline | Remarks
Feedback Items
Candidate Complete Download | Agree dossier contents and format with HR: resume / Zeko report / Evalground report / all round scorecards / recording links | High | Yet-to-start | Staging | Phase 3 | 6 | Week 1 | P0 - Needs clarification on format.
Candidate Complete Download | Backend: per-candidate aggregation endpoint under /api/pipeline/:id/dossier | High | Yet-to-start | Staging | Phase 3 | 6 | Week 1 | P0 - New requirement - today only list-level exports exist (pipeline.routes.js:29 / screening.routes.js:35 / candidate.routes.js:69)
Candidate Complete Download | Generate the downloadable pack (PDF/Excel summary plus attachments) | High | Yet-to-start | Staging | Phase 3 | 8 | Week 1 | P0 - New requirement - downloads everything of candidate's and then shares with any other person over mail/teams'
Candidate Complete Download | Frontend: Download button in PipelineDrawer restricted to recruiter and final decision-makers | High | Yet-to-start | Staging | Phase 3 | 3 | Week 1 | P0 - New requirement - as a recruiter she should have that provision
Candidate Complete Download | Verify the pack opens outside the ATS with no login and leaks no vendor or CTC data | High | Yet-to-start | Staging | Phase 3 | 6 | Week 1 | P0 - New requirement - recipient is an external Technical 3/4 interviewer with no ATS account
Interview Recording Access | Capture the Teams recording link per round - extend the existing manual rpa_interview_scorecard.recording_url and auto-populate where Graph permits | High | Yet-to-start | Staging | Phase 3 | 8 | Week 1 | P0 - Partially implemented - field exists today as a manual paste (InterviewScorecard.jsx:282 / schema.prisma:928)
Interview Recording Access | Role-gate recording visibility to recruiter / HR Head / CEO - hidden from interviewers | High | Yet-to-start | Staging | Phase 3 | 6 | Week 1 | P0 - New requirement - 'for others it is not needed - only when it comes to Sanghamitra and Abhijit'
Interview Recording Access | Surface Technical 1 and Technical 2 recording links in the PipelineDrawer round panels and include them in the dossier | High | Yet-to-start | Staging | Phase 3 | 8 | Week 1 | P0 - New requirement - 'Management needs to be able to see the recordings of these people the technical one technical 2 person'
Referral Candidate | DDL: referral flag and referred_by on the shortlist / pipeline row | Medium | Yet-to-start | Staging | Phase 3 | 4 | Week 1 | P1 - New requirement - zero occurrences of 'referral' anywhere in the codebase today
Referral Candidate | Set the referral flag at shortlist / tag-to-JD time on the keyword-search path | Medium | Yet-to-start | Staging | Phase 3 | 3 | Week 1 | P1 - New requirement - 'it will also show as referred referral candidate'
Referral Candidate | Role-based visibility: recruiter and final decision-maker only - suppressed for every interviewer and on scorecards | Medium | Yet-to-start | Staging | Phase 3 | 4 | Week 1 | P1 - New requirement - 'interviewer can't see. But the recruiter need to see that it is a referral candidate'
Referral Candidate | Verify the referral chip is absent from interviewer payloads / scorecard forms / interviewer emails | Medium | Yet-to-start | Staging | Phase 3 | 4 | Week 1 | P1 - New requirement - 'None of the interview process should know that it is a referred person'
Analytics Screen | Add per-role Total Applied and Moved Forward columns plus the shortlisting ratio | Medium | Yet-to-start | Staging | Phase 3 | 4 | Week 1 | P1 - Partially implemented - per-role counts already computed at screening.service.js:2461-2488 but only global totals are surfaced. Absorbs the existing 'Analytics should show candidate details per role' line on the Phase 4 sheet - Sanghamitra Roy - 'I need both the numbers 100 and 50 - 2 more columns'
Vendor 2 - C2C Vendor | Vendor / Placement upload with no mandatory email or phone - name-only dedup - recruiter review | Low | Yet-to-start | Staging | Phase 4 |  |  | Already on the Phase 4 tasks list (Vendor 2 - C2C Vendor block - 40 rows). Do not duplicate. Sanghamitra Roy: hold until the core runs stable for 1-2 months
MS Access Feasibility / Export | Historical Access database analysis - field mapping - migration or synchronisation | Low | Yet-to-start | Staging | Phase 4 |  |  | Already on the Phase 4 tasks list (4 rows). Sanghamitra Roy - 'we need to integrate that at some point because that is lot of data'
Admin Config UI | Stages / Outcomes / Reasons CRUD so admins edit messages and recipients without a developer | Low | In-progress | Staging | Phase 4 |  |  | Already on the Phase 4 tasks list (3 rows). Harish confirmed in the call - 'we are working on this as well'
External Interview | External reviewer requires data to shared on a mail | Low | Yet-to-start | Staging | Phase 4 |  |  | We should be able to just download the details to forward to external people.
UAT
Candidate Source Categories | Naming and data model for College Placement / Placement / Vendor - DO NOT START until the confirmation row above closes | Medium | Yet-to-start | Staging | Phase 3 - UAT |  |  | P1 - Blocked - 'clear difference info need to get from naveen & chhaya)
Evalground Integration | Obtain Evalground API charges and a customer-support contact | Medium | Yet-to-start | Staging | Phase 3 - UAT |  |  | P2 - Needs clarification - cross verify the amount
Real Hiring Validation | Nominate 3-4 live requisitions and run each end-to-end: upload > screening > shortlist > interview > assessment > final decision | High | Yet-to-start | Staging | Phase 3 - UAT
Real Hiring Validation | Maintain one consolidated defect / process-gap tracker with every item classified P0-P3 | High | Yet-to-start | Staging | Phase 3 - UAT
UAT Onboarding | Brief Chhaya and Naveen and get them testing; both on leave until Tue/Wed | High | Yet-to-start | Staging | Phase 3 - UAT
MRF Approval Defect | Reproduce the production MRF approval failure - capture the exact error text - fix and re-test | High | Yet-to-start | Staging | Phase 3 - UAT |  |  | Sanghamitra Roy approved it and it was not going. It says that something lost.
Screening Validation | Confirm a JD / filter change re-screens previously filtered-out candidates including those excluded on budget | High | Yet-to-start | Staging | Phase 3 - UAT |  |  | Needs validation - Sanghamitra Roy - Harish confirmed live: 'once we update the JD it will automatically updates everything'
Evalground Assessment Import | Confirm the Public Report URL in the Evalground export opens without an Evalground login | Medium | Yet-to-start | Staging | Phase 3 - UAT |  |  | Needs validation - GATES the report-link task below - Sanghamitra Roy - 'we also look at the report in detail'
Scheduling Validation | Teams / Outlook forward-version compatibility check on calendar invites and HTML emails | Medium | Yet-to-start | Staging | Phase 3 - UAT |  |  | Needs validation - Sanghamitra Roy - 'what happens if there is any like just a Teams and Outlook is gets different versions'
Screening Validation | Confirm the LinkedIn profile URL is captured and displayed on real candidates | Low | Yet-to-start | Staging | Phase 3 - UAT |  |  | Already in place - spot-check only