## Sheet1
Task | Task Detail Description | Priority | Status | Environment | Phase | Hours | Timeline | Remarks | Resource
Research
Zeko API Validation (R&D) | Review Zeko API docs/sandbox for score/cheat-probability/report/recording fields & connect with Zeko team if required, Finalize the Outcome | High | In-progress | Staging | Phase 3 | 14 | Week 1 | Unassigned until now single biggest schedule risk in Phase 3
Evalground Import Readiness (R&D) | Verify bulk CSV sample vs Section 1/2/3 design, single-result Outlook report sample | High | In-progress | Staging | Phase 3 | 3 | Week 1 | Sample received 2026-07-14 . High level verification done from Harish.
Evalground Import Readiness (R&D) | Plan - bulk CSV section + skill mapping approach | High | In-progress | Staging | Phase 3 | 2 | Week 1 | Blocks M2 bulk importer UI
MS Graph Calendar Access (R&D) | Submit Graph permission request (Calendars.ReadWrite + Schedule.Read.All) to IT Team + Followup + Testing | High | In-progress | Staging | Phase 3 | 5 | Week 1 | Hard gate on M3a start date
DB
Pipeline Stage Engine- Data base Schema Setup | DDL: rpa_pipeline_stages + rpa_stage_outcomes + rpa_stage_email_templates tables | High | Completed | Staging | Phase 3 | 0.5 | Week 1
Pipeline Stage Engine- Data base Schema Setup | DDL: rpa_candidate_pipeline table + partial unique index (cv_id/mrf_id) | High | Completed | Staging | Phase 3 | 0.5 | Week 1
Pipeline Stage Engine- Data base Schema Setup | DDL: rpa_pipeline_stage_events (append-only audit) table | High | Completed | Staging | Phase 3 | 0.5 | Week 1
Pipeline Stage Engine- Data base Schema Setup | DDL: rpa_outcome_reasons table +New option setup by admin in the UI | High | Completed | Staging | Phase 3 | 0.5 | Week 1
Pipeline Stage Engine- Data base Schema Setup | CHECK-constraint pre-flight DDL (rpa_email_templates.category; pipeline_status) | High | Completed | Staging | Phase 3 | 0.5 | Week 1 | Must run before seeding new categories/values
Pipeline Stage Engine- Data base Schema Setup | prisma db pull + prisma generate + schema review | High | Completed | Staging | Phase 3 | 0.5 | Week 1
Frontend
Pipeline Tracker UI | Email Body Field in the UI before sending email | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Pipeline.jsx kanban board & stage columns rendered from config | High | Completed | Staging | Phase 3 | 2 | Week 1 | Shortlisting is the only entry point no manual add
Pipeline Tracker UI | Candidate cards: aging badge/source tag/status chip/concurrency badge | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Filters + counts | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Route /pipeline behind ModuleRoute | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | PipelineDrawer.jsx round stepper + per-round panel shell | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Outcome modal (mandatory reason dropdown + notes) | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Closure select on the Offer round | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | pipeline.js frontend API client | High | Completed | Staging | Phase 3 | 2 | Week 1
Pipeline Tracker UI | Pipeline analytics tab in existing Analytics.jsx (funnel/aging/rejection reasons) | High | Completed | Staging | Phase 3 | 2 | Week 1 | No new analytics page
Backend
Pipeline Stage Engine | pipelineStages.js config constants (STAGE_KEYS/OUTCOMES/FINAL_OUTCOMES) | High | Completed | Staging | Phase 3 | 2 | Week 2
Pipeline Stage Engine | pipeline.service.js: listPipeline (board data/filters/aging) | High | Completed | Staging | Phase 3 | 4 | Week 2
Pipeline Stage Engine | pipeline.service.js: getPipelineDetail (row + event timeline + emails) | High | Completed | Staging | Phase 3 | 3 | Week 2
Pipeline Stage Engine | pipeline.service.js: setStageOutcome transaction (core write-back engine) | High | Completed | Staging | Phase 3 | 4 | Week 2
Pipeline Stage Engine | pipeline.service.js: advanceStage + setFinalOutcome | High | Completed | Staging | Phase 3 | 3 | Week 2
Pipeline Stage Engine | Cooling-off guard logic (6-month window on new journey creation) | High | Completed | Staging | Phase 3 | 3 | Week 2
Pipeline Stage Engine | Concurrent-MRF journey support (two active journeys, no cross-stop) | High | Completed | Staging | Phase 3 | 3 | Week 2
Pipeline Stage Engine | Legacy write-back: rpa_cv.FinalStatus text (classifyStatus compatibility) | High | Completed | Staging | Phase 3 | 2 | Week 2
Pipeline Stage Engine | Legacy write-back: rpa_shortlisted_candidates.pipeline_status + future_prospect | High | Completed | Staging | Phase 3 | 2 | Week 2
Pipeline Stage Engine | Legacy endpoint delegation (updateCandidateStatus new engine) | High | Completed | Staging | Phase 3 | 3 | Week 2 | No double emails when pipeline row exists
Pipeline Stage Engine | pipeline.controller.js + pipeline.routes.js (CRUD + admin config endpoints) | High | Completed | Staging | Phase 3 | 3 | Week 2
Pipeline Stage Engine | Seed script: seed-pipeline-stages.js (12 stages + reasons + templates) | High | Completed | Staging | Phase 3 | 3 | Week 2
Outcome Email Dispatcher | stageNotification.service.js: template resolution chain | High | Completed | Staging | Phase 3 | 3 | Week 2 | stageoutcome mapping generic fallback
Outcome Email Dispatcher | Vendor dual-send (cc) recipient assembly + staging redirect | High | Completed | Staging | Phase 3 | 2 | Week 2
Outcome Email Dispatcher | rpa_email_messages / rpa_email_tracking / rpa_email_log trio wiring | High | Completed | Staging | Phase 3 | 2 | Week 2
Outcome Email Dispatcher | Ad-hoc per-candidate email override endpoint | High | Completed | Staging | Phase 3 | 3 | Week 2 | New RT ask 2026-07-14 not yet built
Outcome Email Dispatcher | Unit tests: recipient assembly with redirect mocked off | High | Completed | Staging | Phase 3 | 2 | Week 2
Bell Notifications | Socket.io events (pipeline:outcome / awaiting_feedback / assessment:import_done) | High | Completed | Staging | Phase 3 | 2 | Week 2 | In-memory only persistent notification center deferred
Bell Notifications | Frontend NotificationBell wiring for new pipeline events, any other important modules | High | Completed | Staging | Phase 3 | 4 | Week 2
Candidate Pipeline - Testing
M1 Verification/Testing | Staging DDL apply + prisma pull diff review | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Seed run + category CHECK validation | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Outcome-email round trip test (one per type + tracking rows) | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Vendor dual-send unit test (candidate to + vendor cc) | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Legacy regression pass (analytics/status, VendorDashboard buckets, shortlist flow) | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Concurrent-MRF + cooling-off scenario test | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Future Prospect scenario test (Stage 0 write-back + re-shortlist) | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
M1 Verification/Testing | Write docs/CHANGES-phase3-m1-pipeline.md | High | Yet-to-start | Staging | Phase 3 | 0.5 | Week 2
Evalground Backend & Frontend
Evalground Assessment Import | rpa_assessment_imports table (file/counts/mechanism) | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | assessmentImport.service.js bulk CSV parse (existing xlsx dep) | High | Completed | Staging | Phase 3 | 3 | Week 2
Evalground Assessment Import | Section 1/2/3 label handling (admin-renameable, not hard-coded) | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Skip-unless-score-changed retake logic | High | Completed | Staging | Phase 3 | 2 | Week 2 | RT-confirmed rule only score overwritten on retake
Evalground Assessment Import | Candidate match by email (fallback: name+phone review list) | High | Yet-to-start | Staging | Phase 3 | 3 | Week 2
Evalground Assessment Import | Validation preview + commit + import log | High | Completed | Staging | Phase 3 | 3 | Week 2
Evalground Assessment Import | Single-result entry path (Outlook mechanism) | High | Yet-to-start | Staging | Phase 3 | 3 | Week 2
Evalground Assessment Import | Frontend: import action inside Assessment round panel | High | Completed | Staging | Phase 3 | 3 | Week 2 | Never a standalone screen
Evalground Assessment Import | Frontend: Section-label preview + inline rename | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Frontend: validation report (matched/unmatched/malformed) | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Frontend: import history list | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Evalground test pending badge for untested candidates | High | Completed | Staging | Phase 3 | 2 | Week 2 | Never expires/deleted
Evalground Assessment Import | Auto-suggest Passed/Failed at 50% pass mark | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Verification: crafted CSV matrix (matched/unmatched/duplicate/retake/malformed) | High | Completed | Staging | Phase 3 | 3 | Week 2
Evalground Assessment Import | Verification: idempotent re-import test | High | Completed | Staging | Phase 3 | 2 | Week 2
Evalground Assessment Import | Verification: single-result path parity with bulk path | High | Completed | Staging | Phase 3 | 2 | Week 2
Interviews Backend & Frontend
Teams/Outlook Scheduling | calendar.service.js Graph events create/patch/cancel | High | Completed | Staging | Phase 3 | 4 | Week 3 | Needs Calendars.ReadWrite grant
Teams/Outlook Scheduling | Verify Graph grant via scratch script (assert onlineMeeting.joinUrl) | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | rpa_interview_schedules table | High | Completed | Staging | Phase 3 | 2 | Week 3
Teams/Outlook Scheduling | rpa_interview_feedback table | High | Completed | Staging | Phase 3 | 2 | Week 3
Teams/Outlook Scheduling | Schedule endpoints under /api/pipeline/:id/interviews | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | Public no-login scorecard endpoints (token pattern reuse) | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | interviewReminderScheduler.js env-gated cron with agreed cadence | High | Completed | Staging | Phase 3 | 4 | Week 3 | Candidate/interviewer T-30; feedback 1h then every 2 days to day 6 then stop ~day 10
Teams/Outlook Scheduling | Frontend: schedule modal (DatePicker + interviewer picker + free/busy) | High | Completed | Staging | Phase 3 | 4 | Week 3
Teams/Outlook Scheduling | Frontend: InterviewFeedbackForm.jsx Technical/CEO shared card layout | High | Completed | Staging | Phase 3 | 4 | Week 3 | Skills 1-3 mandatory + 4-5 optional; 0.5-step ratings
Teams/Outlook Scheduling | Frontend: InterviewFeedbackForm.jsx HR Round card variant | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | Frontend: feedback review panel | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | Round-status chips wired to schedule + feedback state | High | Completed | Staging | Phase 3 | 2 | Week 3
Teams/Outlook Scheduling | Consolidated feedback text block generation + HR notify | High | Completed | Staging | Phase 3 | 2 | Week 3
Teams/Outlook Scheduling | Second increment: published-slots model + candidate slot-picker page | High | Completed | Staging | Phase 3 | 4 | Week 3 | Interviewer-fixed mode ships first
Teams/Outlook Scheduling | Slot conflict handling (interviewer overwrites published slots) | High | Completed | Staging | Phase 3 | 2 | Week 3
Teams/Outlook Scheduling | Staging safety: substitute attendees for non-prod calendar invites | High | Completed | Staging | Phase 3 | 2 | Week 3 | Email redirect does NOT cover calendar invites
Teams/Outlook Scheduling | Timezone handling (store TIMESTAMPTZ, render IST) | High | Completed | Staging | Phase 3 | 1 | Week 3
Teams/Outlook Scheduling | Verification: full round-trip (schedule invite reminder scorecard email) | High | Completed | Staging | Phase 3 | 4 | Week 3
Teams/Outlook Scheduling | Verification: reschedule + cancel paths | High | Completed | Staging | Phase 3 | 3 | Week 3
Teams/Outlook Scheduling | Verification: confirm no real attendee ever receives staging invites | High | Completed | Staging | Phase 3 | 2 | Week 3
Document Collection | rpa_document_requests table | High | Completed | Staging | Phase 3 | 2 | Week 3
Document Collection | rpa_candidate_documents table | High | Completed | Staging | Phase 3 | 2 | Week 3
Document Collection | Request endpoint + "Document Collection Request" template seed | High | Completed | Staging | Phase 3 | 2 | Week 3 | Exact text received from Chhaya 2026-07-14
Document Collection | Public token-gated multi-file upload endpoint (multer + OneDrive) | High | Completed | Staging | Phase 3 | 3 | Week 3
Document Collection | Verify/reject-with-reason endpoint + auto re-request loop | High | Completed | Staging | Phase 3 | 4 | Week 3
Document Collection | Reminder wiring (email_type=document_request) | High | Completed | Staging | Phase 3 | 2 | Week 3
Document Collection | Archive-to-SharePoint job stub (threshold-driven) | High | Completed | Staging | Phase 3 | 3 | Week 3 | Threshold not yet set build schedulable job only
Document Collection | Frontend: DocumentUpload.jsx (checklist + multi-file) | High | Completed | Staging | Phase 3 | 3 | Week 3 | Blocked/may descope: capacity check pending
Document Collection | Frontend: verification checklist tab in drawer | High | Completed | Staging | Phase 3 | 4 | Week 3
Document Collection | Guard: audit no document data exposed on vendor APIs | High | Completed | Staging | Phase 3 | 2 | Week 3
Document Collection | Verification: end-to-end request upload verify re-request loop | High | Completed | Staging | Phase 3 | 3 | Week 3
Offer Management & Closure | rpa_offers table (record-only no letter file storage) | High | Completed | Staging | Phase 3 | 2 | Week 3
Offer Management & Closure | Approval flow: approval-requested daily nudge in-app approve | High | Completed | Staging | Phase 3 | 3 | Week 3
Offer Management & Closure | Offer shared recording with soft gate for exceptions | High | Completed | Staging | Phase 3 | 2 | Week 3
Offer Management & Closure | Legacy field population (offer_sent_at/offer_accepted_at/joined_at) | High | Completed | Staging | Phase 3 | 2 | Week 3
Offer Management & Closure | 90-day post-Joined auto-close cron (env-gated) | High | Completed | Staging | Phase 3 | 2 | Week 3
Offer Management & Closure | Vendor status-only notification (never letter/figures) | High | Completed | Staging | Phase 3 | 1 | Week 3
Offer Management & Closure | Closure via M1 endpoint + comms | High | Completed | Staging | Phase 3 | 1 | Week 3
Offer Management & Closure | Verification: approval nudge cadence + soft-gate + auto-close | High | Completed | Staging | Phase 3 | 3 | Week 3
Vendor 1 - Placement Vendor
Placement Vendor Completion & Hardening | VendorDashboard real stage column from rpa_candidate_pipeline | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3 | Fallback to classifyStatus for legacy rows
Placement Vendor Completion & Hardening | Isolation audit every pipeline API filtered by VendorEmail | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | Dual-send coverage audit across M2M5 (every send via dispatcher) | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | Vendor sensitive-stage suppression audit (offer/CTC/documents) | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | Cooling-off enforcement audit | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | 90-day lock vs closure interaction check | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | Admin exposure of new templates/reason lists/flow keys | High | Yet-to-start | Staging | Phase 3 | 2 | Week 3
Placement Vendor Completion & Hardening | Docs updates (VENDOR_PROCESS.md + consolidated CHANGES-phase3-*.md) | High | Yet-to-start | Staging | Phase 3 | 1 | Week 3
Placement Vendor Completion & Hardening | Whole-DB skill-search verification (vectorStore.service.js + stage history) | High | Yet-to-start | Staging | Phase 3 | 1 | Week 3 | Non-negotiable RT requirement verify or extend
Analytics Screen
Functional tabs - Role Summary, Pipeline Summary, Email Summary, Recruiter insights |  | High | Yet-to-start | Staging | Phase 3 | 1 | Week 3
Dashboard vs Analytics |  | High | Yet-to-start | Staging | Phase 3 | 1 | Week 3
Reminder Settings |  | High | Yet-to-start | Staging | Phase 3 | 1 | Week 3