## Sheet1
Task | Task Detail Description | Priority | Status | Environment | Phase | Hours | Opinion | Remarks | Resource
Vendor 2 - C2C Vendor
C2C Vendor Creation- Data base Schema Setup | ALTER rpa_users: add vendor_type + contact_number + vendor_skills columns | High | Yet-to-start | Staging | Phase 3 | 1 |  | NULL vendor_type = placement backward-compatible
C2C Vendor Creation- Data base Schema Setup | CREATE rpa_cv_c2c table (no email/phone unique + no lock column) + indexes | High | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation- Data base Schema Setup | CREATE rpa_cv_c2c_tmp staging/review table (LIKE rpa_cv_c2c) + reviewStatus/source/already_in_main_pool columns | High | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation- Data base Schema Setup | ALTER rpa_upload_jobs: add vendor_type column | High | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation- Data base Schema Setup | CREATE rpa_candidates_all shared read view (UNION rpa_cv + rpa_cv_c2c) | High | Yet-to-start | Staging | Phase 3 | 1 |  | Keeps shared tracking/status steps single-sourced
C2C Vendor Creation- Data base Schema Setup | prisma db pull + prisma generate + schema review | High | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation | admin.controller.js: createUser/updateUser accept vendor_type + contact_number + vendor_skills when role=vendor | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | AdminDashboard frontend: Vendor Type select + Contact Number + Skills fields (shown only for Role=Vendor) | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | POST /api/mrf/:id/share-jd endpoint (vendorEmails[] + c2c_rate + contract_duration) | Medium | Yet-to-start | Staging | Phase 3 | 3
C2C Vendor Creation | sendVendorJDEmail - reuse generateMrfEmailTable + append Duration/Rate blocks | Medium | Yet-to-start | Staging | Phase 3 | 2 |  | Rate/Duration required for C2C optional for placement
C2C Vendor Creation | MRF detail view: Share JD button + modal (multi-select vendors + optional Duration/Rate) | Medium | Yet-to-start | Staging | Phase 3 | 3
C2C Vendor Creation | hrUpload.service.js: SOURCE_PROFILE object + c2c_vendor branch at dedup/insert site | Medium | Yet-to-start | Staging | Phase 3 | 4 |  | Shared engine reused - not a fork of the 1724-line runBatchParsing
C2C Vendor Creation | Dedup key logic: name+inMemoryPII match vs rpa_cv_c2c + secondary cross-check vs main rpa_cv | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Flags already_in_main_pool - never auto-merges/rejects
C2C Vendor Creation | Persistence branch: omit EmailID/ContactNumber from rpa_cv_c2c insert (persistPII=false) | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Lock-skip branch: no 90-day lock stamp for C2C (applyLock=false) | Medium | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation | Notify branch: vendor-only alert + suppress candidate welcome/missing-data emails (NDA) | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | vendor.controller.js uploadResumes: route by req.user.vendor_type (c2c_vendor vs vendor_portal) | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | c2cReview.controller.js: POST /c2c-review/merge | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | c2cReview.controller.js: POST /c2c-review/reject | Medium | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation | c2cReview.controller.js: POST /c2c-review/accept-new (expected name-collision path) | Medium | Yet-to-start | Staging | Phase 3 | 2 |  | Name collision in C2C is expected not an error
C2C Vendor Creation | Register c2c-review routes under staff-only guard in vendor.routes.js | Medium | Yet-to-start | Staging | Phase 3 | 1 |  | Review never vendor-accessible
C2C Vendor Creation | Review queue UI: contextual tagging (Name/Vendor/MRF) + already_in_main_pool warning chip | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Never mutate the raw Name field
C2C Vendor Creation | screening.service.js: scoringProfile param - C2C 3-axis weights (Skills/CTC/Notice) | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Education + stability weights zeroed for C2C
C2C Vendor Creation | Gemini prompt scoped to C2C axes only | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | screening.controller.js: GET /api/screening/c2c/search endpoint | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | C2CVendorPortal.jsx - upload screen (no candidate email/phone fields) + NDA banner | Medium | Yet-to-start | Staging | Phase 3 | 4 |  | Reuses existing premium upload components
C2C Vendor Creation | App.jsx: render C2CVendorPortal when vendor_type=c2c on vendor login | Medium | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation | VendorDashboard.jsx C2C variant: hide email/phone columns + read C2C endpoint | Medium | Yet-to-start | Staging | Phase 3 | 3
C2C Vendor Creation | Shared tracking dashboard: wire to rpa_candidates_all view with candidate_type filter | Medium | Yet-to-start | Staging | Phase 3 | 2 |  | No UNION logic needed in controller
C2C Vendor Creation | Verify DDL: no PII/lock columns on C2C tables + shared view returns both categories | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Verify registration: vendor_type/contact/skills persist + existing vendors still resolve as placement | Medium | Yet-to-start | Staging | Phase 3 | 1
C2C Vendor Creation | Verify Share JD: email + portal notification reach vendors + Rate/Duration blocks render | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Verify C2C routing: portal renders + upload runs through shared engine + lands in rpa_cv_c2c with no PII/no lock | Medium | Yet-to-start | Staging | Phase 3 | 3
C2C Vendor Creation | Verify dedup: name collision routes to review + main-pool match flagged + PII never persisted anywhere | Medium | Yet-to-start | Staging | Phase 3 | 3
C2C Vendor Creation | Verify Accept-as-new: both candidates exist independently + contextual tags shown + Name unchanged | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Verify screening: C2C search scores only Skills/CTC/Notice | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Verify notifications: zero emails to any parsed candidate address on C2C upload | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Verify shared steps 7-9: status update appears in shared per-vendor tracking dashboard | Medium | Yet-to-start | Staging | Phase 3 | 2
C2C Vendor Creation | Full placement regression test (dedup + 90-day lock + merge + emails unchanged) | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Proves the shared engine was not regressed
C2C Vendor Creation | VENDOR_PROCESS.md Update Log entry + supersede c2c_vendor_plan.md with as-built section | Medium | Yet-to-start | Staging | Phase 3 | 1
Least Priority/Future Phases
MS Access Feasibility (R&D) | Feasibility write-up (schema-mismatch handling options) & Alternate solution plan | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Blocks M6 MS Access export/import design
MS Access Export (Interim Win) | Scheduled CSV/Excel export job (core candidate tables) | Medium | Yet-to-start | Staging | Phase 3 | 3 |  | Ships regardless of full schema reconciliation outcome
MS Access Export (Interim Win) | Export scheduling/cron wiring | Medium | Yet-to-start | Staging | Phase 3 | 2
MS Access Export (Interim Win) | Verification: export completeness spot-check | Medium | Yet-to-start | Staging | Phase 3 | 2
Prompt Config (For all our prompts) |  | Medium | Yet-to-start | Staging | Phase 3 | 2
Settings Page - For Theme, etc |  | Medium | Yet-to-start | Staging | Phase 3 | 2
All Candidate list (in probably search & Edit candidate page) |  | Medium | Yet-to-start | Staging | Phase 3 | 2
Captcha implementation |  | Medium | Yet-to-start | Staging | Phase 3 | 2
logs should be visible to us- developers. instead of us waiting for the HR team to comeback, we need to get that errors first. |  | Medium | Yet-to-start | Staging | Phase 3 | 2
Admin Config UI | Stages CRUD admin tab | High | Yet-to-start | Staging | Phase 3 | 3
Admin Config UI | Outcomes CRUD (per stage) | High | Yet-to-start | Staging | Phase 3 | 3
Admin Config UI | Reasons CRUD | High | Yet-to-start | Staging | Phase 3 | 2
R&D - if interview already happened to the same candidate 90 days back - we need to either archive/delete from the zeko data.
Website Integration
Analytics should show candidate details per role.
AI in Pipeline and Analytics Page
reminder settings - not are covered entire reminder settings
Dashboard -recent candidates - are not taking to the right selection in the Search Candidates Page